## Export Summary
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Product Backlog | Table 1 | Product Backlog
Sprint Backlog | Table 1 | Sprint Backlog
Stand up Meeting | Table 1 | Stand up Meeting
Retrospection | Table 1 | Retrospection

## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US101 | As a data engineer, I want a normalized flight database so services can query efficiently. | Must Have | DB setup | Backend Team | Completed
Sprint 2 | Sprint 2 | US201 | As a user, I want REST APIs to search flights by origin, destination and date. | Must Have | Database ready | Backend Team | Completed
Sprint 3 | Sprint 3 | US301 | As a user, I want reliable booking with seat selection, payment simulation and unique PNR. | Must Have | APIs ready | Backend Team | Completed
Sprint 4 | Sprint 4 | US401 | As a user, I want a polished UI to complete booking, view PNR and download receipts. | Must Have | Backend & frontend integration | Both Teams | Completed

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US101 | T1 | Design and implement flight DB schema | 2025-10-03 | 2025-10-07 | DB Dev | Data Modeling | Done | 6 | bar: Day 1 to Day 2
US101 | T2 | Seed sample/simulated flight data | 2025-10-10 | 2025-10-10 | DB Dev | Data Seeding | Done | 6 | bar: Day 3 to Day 4
US201 | T3 | Build flight list and search APIs with validation & sorting | 2025-10-15 | 2025-10-13 | Backend Dev | API Development | Done | 12 | bar: Day 9 to Day 11
US202 | T4 | Integrate dynamic pricing factors (demand, time, seats) | 2025-10-24 | 2025-10-20 | Backend Dev | Pricing Engine | Done | 8 | bar: Day 11 to Day 12
US301 | T5 | Implement concurrency-safe booking with PNR | 2025-11-02 | 2025-11-19 | Backend Dev | Booking Workflow | Done | 10 | bar: Day 13 to Day 14
US401 | T6 | Frontend multi-step booking UI + receipts (PDF/JSON) | 2025-11-10 | 2025-11-22 | Frontend Dev | UI Development | Done | 10 | bar: Day 11 to Day 14

## Stand up Meetings
Sprint | Day | Impediments | Action Taken
Sprint 2 | Day 2 | Invalid date input causing 500 on search API | Added request validation and returned 400 with message
Sprint 3 | Day 1 | Intermittent seat double-booking under load | Introduced DB transactions + row-level locks; added retries
Sprint 4 | Day 2 | UI not reflecting dynamic price updates | Bound UI to API and added periodic refresh

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-10-25 | 2025-10-10 | Backend Team | Document DB constraints clearly | Skipping validation while seeding data | Pair on schema reviews | Shared schema/seed guide created
2 | 2 | 2025-10-16 | 2025-10-18 | Backend Team | Define API contracts first | Loose input validation | Add contract tests | Strict validation and tests added
3 | 3 | 2025-11-04 | 2025-11-15 | Backend Team | Stress-test concurrency paths | Manual seat holds in prod DB | Automate load tests | Load tests + isolation tuning
4 | 4 | 2025-11-05 | 2025-11-22 | Frontend + Backend | Wire UI to pricing updates | Rely on full-page reloads | Use incremental refresh | Price auto-refresh implemented